## Project Dashboard
Drone Engineering Project
PROJECT NAME |  |  |  | DATE | PROJECT STATUS | % COMPLETE
Drone |  |  |  | 2024-11-10 | In Progress | 72%
TASK TIMELINE
DASHBOARD DATA
TASK TABLE
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS | STATUS | PRIORITY
Initial Research |  | 2027-09-02 | 2027-09-03 | 2 | Complete | High | Research on Drone types and Features | Not Started | High
Requirements Gathering |  | 2027-09-03 | 2027-09-07 | 5 | Complete | Medium | Determining Project Scope and Material needed | In Progress | Medium
Component Sourcing |  | 2027-09-07 | 2027-09-12 | 6 | Complete | Low | Ordering parts like motors and Propellers, etc | Complete | Low
CAD Design |  | 2027-09-09 | 2027-09-11 | 3 | Complete | Low | Creating #D Model of the Drone | Overdue
Circuit Design |  | 2027-09-11 | 2027-09-15 | 5 | Complete | Low | Designing the circuit board and wiring | On Hold
Prototype Assembly |  | 2027-09-16 | 2027-09-17 | 2 | Overdue | High | Assembling the Drone Prototype
Software Development |  | 2027-09-17 | 2027-09-21 | 5 | In Progress | High | Developing Control Software
Testing & Calibration |  | 2027-09-24 | 2027-10-02 | 9 | In Progress | High | Calibrating sensors and Testing flight stability
Flight Optimazation |  | 2027-10-02 | 2027-10-05 | 4 | In Progress | High | Optimizing flight control and battery usage
Safety Check |  | 2027-10-05 | 2027-10-07 | 3 | On Hold | High | Ensuring all safety protocols are followed
Final Review & Approval |  | 2027-10-06 | 2027-10-09 | 4 | Not Started | High | Reviewing Project and Preparing for Demonstration
Demonstration & Launch |  | 2027-10-10 | 2027-10-10 | 1 | Not Started | Medium | Demonstrating drone to club memebrs and stakeholders.
TASK STATUS % |  |  |  | BUDGET
STATUS | COUNT | % |  | PLANNED | 800
Not Started | 2 | 16.67% |  | ACTUAL | 673
In Progress | 3 | 25%
Complete | 5 | 41.67%
Overdue | 1 | 8.333%
On Hold | 1 | 8.333%
TOTAL | 12 | 100%
TASK PRIORITY % |  |  |  | PENDING ITEMS
PRIORITY | COUNT | % |  | Decisions | 5
High | 7 | 58.33% |  | Actions | 2
Medium | 2 | 16.67% |  | Change Requests | 4
Low | 3 | 25%
TOTAL | 12 | 100%